## Read me
Review triage — thomascheesman.ca (2026-06-12)
This workbook splits the CS-professor review into work. Three sheets: YOUR TASKS (things only you can do, with exact steps), MY TASKS (code I fix under the hood — each marked READY, NEEDS ANSWER, or PROPOSE-FIRST), and QUESTIONS (the one sheet you fill — answer the yellow column in one sitting and most of my blocked tasks unblock).
Already done (round 1, before this review)
Meta descriptions sitewide and VideoObject schema for the two film reels shipped in the earlier triage round — the review confirmed both are live and good. They are NOT repeated below.
How we run it
1) You answer the Questions sheet. 2) You say GO and I start the READY rows immediately (none of them need answers). 3) I ship in small batches, you Purge All after each, and I report what changed. 4) The PROPOSE-FIRST row (desk menu) waits for your explicit yes because it is a BHAG surface.
Companion file: World-History-Currents.xlsx in the Heritage research folder — the seed workbook for the next BHAG.

## Your tasks
# | Priority | Task | Why it matters | Exactly how | Time | Depends on
T1 | P1 | Google Search Console — submit the sitemap, request indexing | Google's index holds only 3 URLs from the OLD site — all dead 404s, including the Rycroft post that still ranks #1 for Rycroft pioneer queries. Nothing from the rebuilt site is indexed. Every other SEO fix waits behind this. | 1. Go to search.google.com/search-console and sign in with the same Google account Site Kit uses. 2. If 'thomascheesman.ca' already appears as a property (Site Kit usually creates it), open it. Otherwise: Add property → URL prefix → https://thomascheesman.ca → Verify (Site Kit makes this automatic). 3. Left menu → Sitemaps → type sitemap.xml → Submit. 4. Use the search bar at the top (URL Inspection): paste each URL below, hit Enter, then click 'Request indexing': • https://thomascheesman.ca/ • https://thomascheesman.ca/hcs/ • https://thomascheesman.ca/family/heritage/ • https://thomascheesman.ca/family/heritage/rycrofts/story/ • https://thomascheesman.ca/family/heritage/dochertys/story/ • https://thomascheesman.ca/family/heritage/map/ (Google caps requests around 10/day — these six are the priority order.) 5. Add bareyourrare.org as a second property and submit its sitemap too — it is currently invisible even for its own name. 6. In two weeks: Indexing → Pages — confirm the new URLs show as Indexed. | 20 min | Do AFTER I ship C1–C3 (redirects + titles) — I'll ping you in chat. Then Google re-crawls into the fixed site, not the broken one.
T2 | P1 | Bing Webmaster Tools — same submission | Bing feeds Copilot and ChatGPT search. Your Bing verification token already ships in functions.php, so this should be one click, no setup. | 1. bing.com/webmasters → sign in. 2. If thomascheesman.ca isn't listed: Add site → choose meta-tag verification → it should pass instantly (the tag is already in your <head>). 3. Sitemaps → Submit → https://thomascheesman.ca/sitemap.xml. 4. Optional but worth it: add bareyourrare.org the same way. | 10 min | Same timing as T1.
T3 | P1 | Hostinger — kill the staging mirror | lightgoldenrodyellow-dugong-336485.hostingersite.com serves a COMPLETE copy of your site. Its robots.txt blocks only Googlebot — Bing and the AI crawlers are explicitly allowed, and its pages point canonicals at themselves. I'm shipping a code guard (C2) that 301s everyone to the real domain, but the cleanest kill is at the host. | 1. hpanel.hostinger.com → Websites → thomascheesman.ca → Manage. 2. Look for 'Temporary domain' (sometimes under Website → Overview, or Domains). If there's a Disable / Redirect toggle, use it. 3. If you can't find a toggle, open the purple live-chat bubble and paste: "Please disable or permanently redirect the temporary hostingersite.com domain for thomascheesman.ca so it can't be indexed by search engines." | 10 min | C2 protects you either way — this is belt and braces.
T4 | P2 | Trash the stray /map-2/ page | A leftover duplicate of the map page is live, indexable, and listed in the sitemap. | wp-admin → Pages → search 'map' → you'll see The Map (parent: Heritage — KEEP) and a stray 'map' with slug map-2 → hover it → Trash. That's it — AIOSEO drops it from the sitemap automatically. (Or say the word and I'll do it through the site's MCP connection.) | 2 min | —
T5 | P2 | Site Kit — switch off 'Sign in with Google' | It loads ~100 KB of render-blocking Google script on every page of the site. Visitors never sign in to anything — only you do, at wp-admin. | wp-admin → Site Kit → Settings → Connected services → 'Sign in with Google' → Manage / three-dot menu → Disconnect. Leave Search Console and Analytics connected (Analytics pending your Q7 answer). | 3 min | —
T6 | P2 | WonderPush — decide, then (maybe) remove | 93 KB of push-notification code rides every page. Only worth it if you actually send pushes. | Answer Q6 first. If dropping: wp-admin → Plugins → WonderPush → Deactivate → Delete. Done — no other cleanup needed; I'll confirm the scripts are gone after. | 3 min | Q6
T7 | P3 | Register bareyourrare.ca and forward it | The .ca is unregistered — anyone could take the Canadian domain of your nonprofit's name tomorrow. (And in search, the name currently belongs to a K-pop album.) | If Q16 = yes: Hostinger → Domains → Get a New Domain → bareyourrare.ca (~$15–20/yr) → after purchase: Domains → bareyourrare.ca → Forwarding/Redirect → 301 → https://bareyourrare.org. | 15 min | Q16
T8 | P1 | Answer the Questions sheet — the big swoop | 21 questions, prioritized, each with context and my recommendation. Most of my blocked tasks unblock the moment this comes back. | Fill the yellow 'YOUR ANSWER' column. Short answers are fine — 'yes', 'B', 'rewrite: …'. Anything you skip I'll treat as 'decide later', not 'no'. | 30–45 min | —
T9 | P3 | Send the press-link email (I draft it) | The Canadian Press article quoting you ran in 7+ outlets with zero links to your site. One added link from a national outlet is the single best backlink available to you, for free. | If Q17 = yes, I'll draft a 4-sentence note to the reporter (thanking them, pointing at /hcs/ as the patient-perspective resource, asking if the online piece can link it). You paste it into your email and send. | 5 min | Q17 + C3 titles live
T10 | P3 | Society outreach — three emails (I draft them) | SGGEE (Volhynia Germans), the Ó Dochartaigh Clann Association, and South Peace Regional Archives are the three communities most likely to LINK to and cite the long-reads. Genealogy backlinks are what make surname pages rank. | If Q21 = yes I draft three short notes, each pointing at the relevant story page and offering the research as a resource (and asking nothing in return). You send from your address. | 15 min | Q21 + C3 titles live
T11 | P2 | Phone pass — the checks automation can't do | I could not drive a real phone. Fifteen minutes with yours closes the gap. | On your phone, in order: 1) Open the site menu — does the accordion feel right? Try the search. 2) Open the Dochertys story — are pull-quotes readable over the magenta in daylight? 3) The map: pinch-zoom, scrub, press Play, tap a lantern. 4) Play both film reels (Haiste + Lakeman) and a crest video — confirm playback and sound. 5) On DESKTOP, open the junk drawer once more after my batches ship. Tell me anything that feels off. | 15 min | Best after my first two batches.
T12 | P3 | Standing items from V0.25 (reminder, nothing new) | Carried so this workbook is the one list. | • The three DOCXs are still with you: Patience-Page-Text, Daniel-Page-Text, Cheesman-Ch7-Cooking-Years (lay-on happens when they return). • family-map-data.xlsx gaps: Melanie's Edmonton years (her answer), Dan's life points (the Papa Dan interview). | — | —
T13 | P1 | LiteSpeed Purge All after each of my batches | You know this one — stale cache is the #1 'did it deploy?' trap. | Admin bar → LiteSpeed Cache → Purge All. I'll say in chat exactly when a batch lands. | 10 sec each | —

## My tasks
# | Priority | Status | Task | What I'll do | Risk | Blocked by
C1 | P1 | READY | 301-redirect the three dead legacy URLs | functions.php template_redirect: /2024/08/29/how-did-rycroft-get-its-name/ → /family/heritage/rycrofts/story/ · /hajdu-cheney-syndrome/ → /hcs/ · /2024/09/13/the-cheesmans/ → /family/heritage/cheesmans/. Recovers the proven #1 Rycroft ranking before Google drops it. | Low | —
C2 | P1 | READY | Staging-host guard | If the request host is the hostingersite.com temp domain: 301 to the same path on thomascheesman.ca + X-Robots-Tag noindex as a fallback. Closes the duplicate-site leak no matter what Hostinger support says. | Low | —
C3 | P1 | NEEDS ANSWER | Unique page titles | aioseo_title filter keyed by page URI — the exact same pattern as the descriptions block at functions.php:598, so titles live in git too. All five hub long-reads currently share the title 'Story - thomascheesman.ca'. Drafts for your veto are in Q2. | Low | Q2
C4 | P1 | NEEDS ANSWER | Social share images (og:image / twitter:image) | Emit a per-page social image (each page's lead image) + a sitewide default. Today every share of every page renders as a bare text card. | Low | Q3
C5 | P1 | READY | Fix the silently-dropped defer | WordPress drops the defer strategy because main.js and the desk scripts are enqueued without one — so GSAP, three.js, and friends block render on every page (~5s of mobile savings measured). Re-enqueue the whole chain with array('in_footer'=>true,'strategy'=>'defer') and verify the attribute actually lands in the HTML. | Medium — needs live load-order testing; I'll verify each init still fires. | —
C6 | P2 | READY | Converter pass + regenerate all 8 story bodies | _md2heritage.js: (a) linkify the in-prose cross-references ('traced three more generations in the Steinke story' becomes a real link — there are a dozen of these); (b) 'Next line →' footer in each line's pastel; (c) a lantern link to the map in every story header; (d) first image eager + fetchpriority=high (the Docherty LCP is a 931 KB lazy-loaded JPEG — 14.5 s); (e) width/height on all story images; (f) swap full-size images to WP's 1536px intermediates with srcset. Regen verified by word-diff per the V0.24 rule. | Medium — touches all 8 pages, but the regen discipline exists for exactly this. | —
C7 | P2 | READY | Heading hygiene | The desk overlay injects an h1 ('Contents') plus nav h2s BEFORE the real h1 on every page — the first heading every crawler reads sitewide is 'Contents'. Demote overlay/drawer headings to styled divs with aria-labels. Zero visual change. | Low | —
C8 | P2 | READY | Contrast scrims on the vivid lines | Subtle radial darkening behind long-read deks and pull-quotes (the pale italics over full-chroma magenta flirt with WCAG failures), plus a label strip behind the family-tree flag-chip text. Screenshots to you after — taste call stays yours. | Low | —
C9 | P2 | READY | Map polish round | (a) Reserve min-height for the drawer footer on the map template — desktop CLS 0.24 → ~0; (b) check the play/pause button label against the text-fill rule (the label looked blank mid-Play in my session — same genre as the 1.0.525 bug); (c) dek copy fix pending Q14. | Low | Q14 for (c) only
C10 | P2 | READY | Curated llms.txt | Serve a hand-written llms.txt via parse_request (same mechanism as the Bing-token route): real page titles, a one-paragraph summary per family line, a note explaining the Verified/Probable/Inherited/Living-memory vocabulary. Replaces the plugin's auto-list where all five stories are named 'Story' and /map-2/ appears. | Low | —
C11 | P2 | READY | Schema wiring (Article + Person + conservative medical) | Article on the 8 long-reads (headline, author → the existing #thomas Person, dates, lead image, wordCount, citation strings for the named records); author wiring on /about and /hcs; on /hcs a MedicalCondition as the page's 'about' entity — name, alternateName, sameAs → OMIM 102500 / Orphanet 955 / GeneReviews. Nothing clinical beyond identification — patient-perspective Article posture, deliberately. | Low | —
C12 | P3 | READY | three.js lazy-load | Load three.js the way pinball already loads Matter.js — on idle, just before the WebGL init — instead of shipping 121 KB (wire) to every visitor up front. Do after C5 so the wins are measured separately. | Medium | After C5 is verified
C13 | P3 | NEEDS ANSWER | Leaderboard hygiene | Name filter in inc/games-leaderboard.php (2–12 chars + blocklist) and wipe the 'erftghfh' Pac-Man entry if you approve. | Low | Q18
C14 | P3 | READY | Stop advertising the WP version | Remove the generator tag from head + feeds. Thirty-second hardening. | Trivial | —
C15 | P3 | READY | noscript fallback | A visible link to the sitemap/footer nav when JS is off — currently a no-JS visitor gets prose but no navigation. | Trivial | —
C16 | P3 | NEEDS ANSWER | Print stylesheet for the long-reads | Phase 1 of the books idea: the stories print/PDF cleanly from the browser (atmospheres off, chips expanded, Notes open). | Low | Q19
C17 | P2 | PROPOSE-FIRST | Heritage line on the desk CONTENTS | The desk monitor lists 8 entries; the 51,000-word heritage project isn't one of them. One added line ('Where we all came from … 203'). BHAG surface, so it waits for your explicit yes + label choice in Q4 — and the ChatGPT-brainstorm offer stands if you want wilder ideas while we're in there. | Low once approved | Q4
C18 | P1 | NEEDS ANSWER | Home page front door | Implement the hero rewrite (Q1) and replace the three boilerplate card blurbs (Q15). The review's verdict: the site fails the 10-second test at the only URL where that's expensive. | Low | Q1, Q15
C19 | P2 | NEEDS ANSWER | Heritage hub upgrades | Copy each story's kicker onto its hub card ('Thirteen generations · Yorkshire to the Peace Country · c. 1610 – today' currently lives only on the story pages); replace the stale Steinke blurb (draft in Q11); link 'send it my way' to /contact (that part is READY and I'll just do it). | Low | Q11
C20 | P2 | NEEDS ANSWER | Manuscript syncs at the source | Two one-line edits at the md source + regen: Rycroft Ch.6 still says the Steinkes are 'not yet traced past' Henry and Martha (its own descent chip disagrees); the Steinke dek opens as a changelog ('As recently as the morning of 10 June 2026…'). Your words — your sign-off first. | Low | Q12, Q13
C21 | P2 | NEEDS ANSWER | Voice round: /about + the recycled sentences | About-Page-Text.docx (same workflow as Daniel's) fixing the broken sentences and de-duplicating the five passages recycled verbatim across /about–/hcs–/thomas, plus the one kid-page 'three words' rework if you pick one. You annotate; I lay on. | Low | Q9, Q10
C22 | P3 | NEEDS ANSWER | GEDCOM / dataset downloads per line | Generated from the descent-tree data the converter already owns, living people excluded. This is what earns genealogist backlinks. | Low | Q20
C23 | P3 | NEEDS ANSWER | PDF book exports | One per line, from the print stylesheet — an archive artifact for the kids' shelves. | Medium | Q19, after C16
— | — | NOTE | Already shipped before this review (round 1) | Meta descriptions sitewide + VideoObject schema on the two film reels. Confirmed live by the review — not repeated here. | — | —

## Questions
Q# | Priority | Topic | Question | Context — what I saw / why it matters | Options / my recommendation | YOUR ANSWER
Q1 | P1 | Home hero | The hero types out: 'Welcome to TC 'ventures — Exploring life, family, and what matters most to me.' Which direction replaces it? | A stranger learns nothing in the first 10 seconds — not the kids, not HCS, not the 400 years of records. The three facts that make this site unlike any other are all below the fold, in boilerplate. | OPTION A — promote your own line from /family: 'Eight family lines, a handful of stories, and the things I want my kids to be able to find later if they go looking.' OPTION B — first person: 'I'm Thomas Cheesman — chef until my hands retired me, dad of three, one of fewer than fifty people alive with Hajdu-Cheney syndrome. This is what I'm leaving them, written while I can.' OPTION C — you write it. My rec: B as the hero, A as the line under it. | your rec sounds right to me
Q2 | P1 | Page titles | Approve or edit these title drafts (each ends '¦ thomascheesman.ca'): | All five hub long-reads share the literal title 'Story - thomascheesman.ca' — invisible in search results, tabs, and bookmarks. Home wastes its title on 'Home -'. | • Home: 'Thomas Cheesman — a life, three kids, eight family lines' • Map: 'The Lanterns of Record — 400 years of family history, mapped' • Cheesmans: 'The Cheesmans — Turner Valley to Teepee Creek, the chosen name' • Dochertys: 'The Dochertys — Donegal to Alberta, nine generations' • McIvers: 'The McIvers — cleared from the Hebrides to the prairie' • Lakemans: 'The Lakemans — Beemster to Calgary, eleven generations' • Verbooms: 'The Verbooms — Suzanna's people of Ter Aar' • Rycrofts: 'The Rycrofts — Leeds, Hawai'i, and the town drawn from a hat' • Steinkes: 'The Steinkes — German Poland to the prairie, fifteen children' • Haistes: 'The Haistes — thirteen generations, Yorkshire to the Peace Country' Edit any line; 'yes' approves the lot. | yes
Q3 | P1 | Share image | (a) Which image is the sitewide default when a page has no obvious lead photo — the desk photo, the family-tree art, or a Dalyn-2024 family photo? (b) OK to auto-use each page's lead image otherwise? | There is no og:image anywhere — every share of every page (texts, Facebook, Discord) renders as a plain text card on an image-rich site. | My rec: desk photo as default (it IS the site's identity), auto lead-image per page. | the desk photo
Q4 | P1 | Desk CONTENTS | Add one Heritage line to the desk monitor's CONTENTS? Pick the label + the fake page number. And do you want the ChatGPT brainstorm prompt for desk placement of The Map object at the same time? | The desk CONTENTS lists 8 entries; the heritage project — 51,000 words — isn't one of them. A visitor who never clicks 'View as a plain list' can leave without learning it exists. (BHAG surface — nothing happens without your yes.) | Label options: 'Where we all came from' / 'The family lines' / 'Heritage'. My rec: 'Where we all came from … 203'. Brainstorm prompt: your call — it earned its keep on the desk-menu build. | your rec sounds right to me
Q5 | P1 | Bitcoin ticker | The live BTC price sits in the header of every page — including /hcs and the kids' pages. (A) remove · (B) move it into the desk as an easter egg on the Bitcoin-books hotspot · (C) keep as is. | It's the one element of chrome that reads as a different site, and it dates every screenshot. The books on the desk are you and they stay regardless. | My rec: B — keep the joke, lose the chrome. | b
Q6 | P1 | Web push | Have you ever sent a push notification through WonderPush? Keep it or drop it? | 93 KB of JS on every page view for a feature that only pays if you use it. | My rec: drop unless you have concrete plans. | drop
Q7 | P1 | Analytics | Do you actually look at Google Analytics? Keep gtag or drop it? | 160 KB — the single largest script on the site. Site Kit's Search Console stats (which you keep either way) cover 'is anyone finding me'. | My rec: keep only if you check it at least monthly. | keep
Q8 | P2 | Township 71 date | What month/year did Township 71 actually close? | /family/thomas says 'nine months in' (≈Aug 2015); /family/daniel says Daniel — born June 30, 2015 — 'showed up just after Township 71 closed its doors.' Both can't be right, and the kids will eventually notice. | Give me the real month and I'll fix whichever page is wrong. | It closed down end of May but I stayed to shut everything down and clean up until the end of the month. Then I took the 2 months off before starting to work at Majors and Tractor Jacks.
Q9 | P2 | 'Three words' device | All three kid pages use the same 'if you held me to three words' scaffold. Rework one? Which? | Read individually: charming. Read by the actual audience — three siblings comparing their pages — the template shows. | My rec: rework Patience's (first-written) into a different device; Daniel's and Faith's stay. Or tell me it's a deliberate family form and we keep all three. | keep daniels. He has the 2 sets and I like that. What can I say about the girls?
Q10 | P2 | /about pass | OK to deliver About-Page-Text.docx (the Daniel workflow) for your edit? | It would fix the broken sentences ('what grew to become our handsome boy', the verbless Steakology fragment, the college-semester clause) and de-duplicate the five sentences that appear word-for-word on /about, /hcs, and /thomas ('Three sites in eighteen months…', 'funny to type given that I'm not a programmer', etc.) — each page keeps the story, each telling gets its own details. | My rec: yes — it's the same grounded de-listing pass that worked for Daniel's page. | yes
Q11 | P2 | Steinke hub card | Approve/edit this replacement blurb: | The card still says 'A line still being traced' — written before the 1858 akte breakthrough, your biggest research win. The card is underselling the best detective story on the site. | DRAFT: 'Origins unknown no more — one evening of records work dropped the floor three generations: an 1858 parish akte in central Poland, fifteen children, and Nana Bette.' | approve
Q12 | P2 | Rycroft Ch.6 sync | Approve a one-line manuscript edit? | Rycroft Ch.6 still says the Steinkes are 'not yet traced past' Henry and Martha — while the descent chip on the SAME page says they're traced three more generations. The breakthrough outran the prose. | Proposed: change the clause to point at the Steinke story ('…now traced three further generations — that story has its own page'). Exact wording shown to you before regen. | approve
Q13 | P2 | Steinke dek | OK to rewrite the dek as story and fold the discovery-night excitement into the body? | The dek opens 'As recently as the morning of 10 June 2026 this page went no further back than Bette's parents…' — a changelog, not a story, and 'tonight' will read strangely in 2046. Every fact stays; the thrill moves into the chapter where it belongs. | My rec: yes. Draft to you before regen. | yes
Q14 | P2 | Map dek arithmetic | The map dek says 'two and a half centuries'; the button says 'play the 400 years' (1610–2030). Fix the dek to 'four centuries' — or was 250 intentional? | Spotted live. If 250 was deliberate (prairie-era framing?) tell me the intent and I'll leave it. | My rec: 'four centuries'. | four centuries
Q15 | P2 | Home cards | OK for me to draft replacements for the three pillar blurbs, in your register, for your edit? | 'Life's greatest joy comes from the people we love' / 'Giving back matters' are the last AI-boilerplate sentences on the site — v1 scaffold copy everything else outgrew. | Example direction — Family: 'Three kids, eight family lines, four hundred years of records. Start here if you're new.' My rec: yes, drafts in the next DOCX round. | YES!
Q16 | P3 | bareyourrare.ca | Register it (~$15–20/yr) and 301 it to bareyourrare.org? | Unregistered today. A Canadian nonprofit whose .ca anyone can buy is a brand risk — and the name is already swamped in search by a K-pop album ('Bare & Rare'). | My rec: yes. | yes
Q17 | P3 | Press email | Want me to draft the link-request note to the Canadian Press reporter? | The Oct 2024 disability-benefit article quoting you syndicated to 7+ outlets (Global News, etc.) — none link your site. One added link is the best single backlink available to /hcs/. | My rec: yes — 4 sentences, you send it. | I wrote so many I don't recall this one specifically, can I see the article and yes, I should send an email
Q18 | P3 | Arcade leaderboard | Wipe the 'erftghfh' Pac-Man score? Add a name filter (2–12 chars + blocklist)? | The keyboard-mash entry proves the leaderboard accepts junk; the first time a kid's friend finds it, it'll accept worse. | My rec: yes to both. | yes to both
Q19 | P3 | Books | Want print stylesheets + per-line PDF 'book' exports? Which line first? | These are books; let them be held. A printed Docherty story on a shelf survives every hosting bill. | My rec: yes; Dochertys first (longest, most-sourced). | yes
Q20 | P3 | GEDCOM downloads | Comfortable publishing the descent data as downloadable GEDCOM/CSV per line — with living people EXCLUDED? | Records would end at the 1991 generation. Downloadable data is what makes other researchers cite and link the site — the genealogy-backlink engine. | My rec: yes, living excluded, tiers carried as notes. | yes
Q21 | P3 | Society outreach | OK to draft the three intro emails (SGGEE, Ó Dochartaigh Clann Association, South Peace Regional Archives)? | The three communities most likely to genuinely value the work — and link it. Goes out after titles ship so the links land on real names, not 'Story'. | My rec: yes. | yes